## Distribution
Member | Java | React | Android | ML | Deployment | Remarks
Li Yuan |  |  | Y | Y | Y
Ziyou | Y | Y | Y
TingTing | Y |  | Y
Amber |  | Y
Nyan | Y |  |  |  |  | (Login/Logout/APIController)
Aung | Y |  | Y
Somik | Y |  | Y |  | Y | Assist on request for react & ML

## NYAN
25.7.2022 | 1.Attend Briefing 2.Group Design meeting
26.6.2022 | 1.Create JwtAuthenticationController(login,Logout) 2.Spring Security 2.Create JWT for REST API 3.Register new User
2022-07-27 | 1.fixed bugs 2.added checking existing user with same username and password in register user api 3.changed api naming
2022-07-28 | 1.Changed ReactJS Register User form 2. fixed variable naming 3. Set up business login and REST API for Frontend
2022-07-29 | 1.Bugs fixed 2.Set up business login and finished Book REST API for frontend
Sprint 1 week
2022-08-01 | 1.Meeting with Prof Cher Wah 2. fixed jwt ciruclar code 3. create event rest api
2022-08-02 | 1. research websocket 2. test websocket in backend
2022-08-03 | 1. add message api(CRUD)
2022-08-04 | 1.work with tingting to create retrieve studygroups with userId api 2. add attributes to userDTO
2022-08-05 | 1.Add Error message for security related error
Sprint 2 week
2022-08-08 | 1. extend jwt time to 90 days 2. change create event with event response 3. add participants in event response
2022-08-10 | 1. Created user join event api 2. added auth check for user update info,password,interest edit 3. fixed join event duplicate 4. fixed join group duplicate
2022-08-11 | 1. add one to one chat message api and logic
2022-09-12 | 1. add groups sorting by time in getting all groups api 2. bugs fixed
Sprint 3 week
2022-08-15 | 1.added check existing individual chat group api 2. added create new or retrieve existing individual group api 3. added create individual message for individual group api 4. added retrieve all message from individual group api 5. added retrieve all individual groups by user as participant
2022-08-16 | 1. add retrieve messages by groupId with pagination api 2. change private group name
2022-08-17 | 1. API documentation 2. recording video for submission
2022-08-18 | 1. create api to retrieve all message by userid and number of days 2. create api to retrieve all message by userid , groupid and number of days 3. create api to get detail dashboard message by userid and number of days 4. Write AD project group report and github readme 5. bug fix on same username or email check 6. API documentation 7. Make video for submission

## Li Yuan
Project | StudyBuddy
Student | Cheong Li Yuan
Sprint 0 Duration | 25/7/2022 - 29/7/2022
|  | Task | Plan | Actual
25/7/2022 | Monday | Attend Briefing | 1 | 1
|  | Group Design meeting | 7 | 7
|  | Total | 8 | 8
26/7/2022 | Tuesday | Prototype sentiment analysis(python ML) | 7 | 7
|  | Meeting with Prof Cher Wah | 1 | 1
|  | Total | 8 | 8
27/7/2022 | Wednesday | Write code for web scraping textbooks | 8 | 8
|  | Total | 8 | 8
28/7/2022 | Thursday | Write code for web scraping textbooks | 8 | 8
|  | Total | 8 | 8
29/7/2022 | Friday | Port textbook data to java backend | 4 | 4
|  | Research on textbook recommendations | 4 | 4
|  | Total | 8 | 8
Sprint 1 Duration | 1/8/2022 - 5/8/2022
2022-01-08 | Monday | Backend code for MLserver(flask) | 8 | 8
|  | Total | 8 | 8
2022-02-08 | Tuesday | Java backend API to support textbook recommendations | 4 | 4
|  | Android code to get/parse java API for textbook recommendations | 4 | 4
|  | Total | 4 | 4
2022-03-08 | Wednesday | Android code to get/parse java API for textbook recommendations | 8 | 8
|  | Total | 8 | 8
2022-04-08 | Thursday | Android/Java/Python codes to to support textbook search functionality | 8 | 8
|  | Total | 8 | 8
2022-05-08 | Friday | Android/Java/Python codes to to support textbook search functionality | 0 | 4
|  | Android: code to support images for chat messages | 8 | 4
|  | Total | 8 | 8
Sprint 2 Duration | 8/8/2022 - 12/8/2022
2022-08-08 | Monday | Android: code to support images for chat messages | 0 | 4
|  | Supporting code to make change of user interests trigger rechecking of book ordering | 4 | 4
|  | Total | 0 | 8
2022-09-08 | Tuesday(National Day) |  | 0 | 0
|  | Total | 0 | 0
2022-10-08 | Wednesday | bug fixes etcetcetc | 0 | 4
|  | ..and more bug fixes | 0 | 4
|  | Total | 0 | 8
2022-11-08 | Thursday | Minor graphical edits: Android border text color post sentiment analysis. Android app icon | 4 | 4
|  | Bug fixes | 0 | 4
|  | Total | 4 | 8
2022-12-08 | Friday | Rescrape textbooks/debug changes for change in requirement | 0 | 4
|  | Debugging | 0 | 4
|  | Total | 0 | 8
Sprint 3 Duration | 15/8/2022 - 19/8/2022
15/8/2022 | Monday | App testing/bug finding/bug fixing | 8 | 8
|  | Total | 8 | 8
16/8/2022 | Tuesday | App testing/bug finding/bug fixing | 8 | 8
|  | Total | 8 | 8
17/8/2022 | Wednesday | Do video presentation | 8 | 8
|  | Total | 8 | 8
18/8/2022 | Thursday | Written report etc | 8 | 8
|  | Total | 8 | 8
19/8/2022 | Friday |  | 0 | 4
|  |  | 0 | 4
|  | Total | 0 | 4
Note | Minimum 6.5 man-hours per day per person
Fill in the timesheet at the end of the day at 5pm

## Khan Sher Mostafa Somik
Project | StudyBuddy
Student | Khan Sher Mostafa Somik
Sprint 0 Duration | 25/7/2022 - 19/8/2022
|  | Task | Plan | Actual | Sprint
2022-07-25 | Monday | Attend Briefing | 1 | 1 | 0
|  | Group Design meeting | 7 | 7
|  | Total | 8 | 8
2022-07-26 | Tuesday | Android entity mapping, getters, setters, constructors | 4 | 3 | 0
|  | Create docker compose files for deployment on cloud | 4 | 8
|  | Total | 8 | 11
2022-07-27 | Wednesday | Develop Python REST API webserver | 6 | 5 | 0
|  | Intregrate python webserver with ML | 2 | 2
|  | Total | 8 | 7
2022-07-28 | Thursday | Android all activity layouts | 6 | 5 | 0
|  | Android Listview adapters | 2 | 2
|  | Total | 8 | 7
2022-07-29 | Friday | Android activities for profiles, books | 4 | 4 | 0
|  | Android API communication class | 4 | 8
|  | Total | 8 | 12
2022-08-01 | Monday | Android activities for groups | 3 | 2 | 1
|  | Android activities for chats | 3 | 2
|  | Deploy app on oracle cloud as docker stack | 2 | 6
|  | Meet prof CW | 1 | 1
|  | Total | 9 | 11
2022-08-02 | Tuesday | Android login activity | 4 | 4 | 1
|  | Android util class for calling API to login | 4 | 6
|  | Total | 8 | 10
2022-08-03 | Wednesday | Android utils for getting groups | 4 | 3 | 1
|  | Deploy ML on docker container | 2 | 5
|  | Create util class in java for calling ML | 2 | 2
|  | Total | 8 | 10
2022-08-04 | Thursday | Android create DTOs | 3 | 2 | 1
|  | Rewrite API communication class to work with DTOs | 5 | 4
|  | Fix Java UserController | 1 | 2
|  | Total | 9 | 8
2022-08-05 | Friday | Rewrite activity switching | 2 | 2 | 1
|  | Fix bugs on android groups & chats | 4 | 2
|  | Add android API comms for Event Listing | 2 | 4
|  | Total | 8 | 8
2022-08-08 | Monday | Android fix app crash when chat is empty | 1 | 1 | 2
|  | Replace UI for activity switching | 1 | 1
|  | Android API comms for change password & register | 4 | 6
|  | Add android API comms for creating event | 2 | 3
|  | Java added file upload support with nginx for file retrival | 6 | 4
|  | Meet prof CW | 1 | 1
|  | Total | 15 | 16
2022-08-10 | Wednesday | Android add background service for checking messages | 5 | 4 | 2
|  | Add notification triggering on new message on groups | 3 | 3
|  | Android implement file pick & upload support | 6 | 8
|  | Android add file upload to java backend | 2 | 4
|  | Total | 16 | 19
2022-08-11 | Thursday | Android fix multipart file uploading | 2 | 5 | 2
|  | Android add webViews for images/videos on chats | 4 | 4
|  | Show images/video on full screen on click | 2 | 2
|  | Total | 8 | 11
2022-08-12 | Friday | Android validate user before login | 4 | 3 | 2
|  | Android add image/video upload support for chats | 4 | 6
|  | Total | 8 | 9
2022-08-15 | Monday | Android add image/video upload support for chats in background | 4 | 5 | 3
|  | Fix bugs running on real hardware | 2 | 3
|  | Meet prof CW | 1 | 1
|  | Fix file java backend to serve file with MIME type for download | 2 | 3
|  | Total | 9 | 12
2022-08-16 | Tuesday | Bug fixes on android 1to1 groups & chats | 4 | 4 | 3
|  | Fix android app crashes on chat activity | 4 | 4
|  | Android fix interests checkbox not getting checked | 1 | 1
|  | Total | 9 | 9
2022-08-17 | Wednesday | Android fix multiple notifications per group | 4 | 4 | 3
|  | Java backend fix file upload with https support | 4 | 4
|  | Report create system architecture | 2 | 2
|  | Make video for submission | 1
|  | Total | 10 | 10
2022-08-18 | Thursday | Bug fixes and testing | 7 | 7 | 3
|  | Make video for submission | 1 | 1
|  | Total | 8 | 8
2022-08-19 | Friday | Bug fixes and testing | 7 | 4 | 3
|  | Work on report | 1 | 4
|  | Total | 8 | 8
Note | Minimum 6.5 man-hours per day per person
Fill in the timesheet at the end of the day at 5pm

## Aye Mya Phoo
Project | StudyBuddy
Student | Aye Mya Phoo (Amber)
|  | Task | Plan | Actual
Sprint 0 Duration | 25/07/2022 - 29/07/2022
25-07-2022 | Monday | Attend Briefing | 1 | 1
|  | Group Design meeting | 7 | 7
|  | Total | 8 | 8
26-07-2022 | Tuesday | Created Frontend (React) Template, add api template | 6.5 | 6.5
|  | Total | 6.5 | 6.5
27-07-2022 | Wednesday | Add Login & Register, Add UI library | 6.5 | 6.5
|  | Total | 6.5 | 6.5
28-07-2022 | Thursday | Add Mock Chat UI & Event List using Calendar | 6.5 | 6.5
|  | Total | 6.5 | 6.5
29-07-2022 | Friday | Add Mock Book UI & Study Group UI | 6.5 | 6.5
|  | Total | 6.5 | 6.5
Sprint 1 Duration | 01/08/2022 - 05/08/2022
2022-01-08 | Monday | Create Chat UI for android using RecyclerView | 4 | 4
|  | Integrate with book api | 3 | 3
|  | Total | 7 | 7
2022-02-08 | Tuesday | Fix cors issue for REACT and | 4 | 4
|  | Add search feature for book | 3 | 3
|  | Total | 7 | 7
2022-03-08 | Wednesday | Attend Meeting | 1 | 1
|  | Create Event, View Event, Display Event in REACT | 6 | 6
|  | Total | 7 | 7
2022-04-08 | Thursday | Attend Meeting | 1 | 1
|  | Create Event, View Event, Display Event in Android | 6 | 6
|  | Total | 7 | 7
2022-05-08 | Friday | Attend Meeting | 1 | 1
|  | Refactor Event in android, Integrate Account Page in React | 6 | 6
|  | Total | 7 | 7
Sprint 2 Duration | 08/08/2022 - 12/08/2022
2022-08-08 | Monday | Attend Meeting | 1 | 1
|  | Upload Profile image, Integrate Book Search using api | 6 | 6
|  | Total | 7 | 7
2022-10-08 | Wednesday | Attend Meeting | 1 | 1
|  | Integrate Chat api in react (send message, send file) | 6 | 6
|  | Total | 7 | 7
2022-11-08 | Thursday | Attend Meeting | 1 | 1
|  | Redesign Tab Layout for Android, Add EventTime for Android | 6 | 6
|  | Total | 7 | 7
2022-12-08 | Friday | Attend Meeting | 1 | 1
|  | Redesign ProfilePage for Android, minor ui changes for Android | 6 | 6
|  | Total | 7 | 7
Sprint 3 Duration | 15/08/2022 - 19/08/2022
15/8/2022 | Monday | Attend Meeting | 1 | 1
|  | 1. Add validation for all create requests in React 2. Add join event or view discussion of event in React | 8 | 8
|  | Total | 9 | 9
16/8/2022 | Tuesday | Attend Meeting | 1 | 1
|  | 1. Add fullscreen view of image and video in React 2. Redesign Chat UI to make responsive UI in react 3. Add search user and one to one chat in React | 8 | 8
|  | Total | 9 | 9
17/8/2022 | Wednesday | Attend Meeting | 1 | 1
|  | 1. Fix UI issue in React 2. Add template for dashboard UI | 8 | 8
|  | Total | 9 | 9
18/8/2022 | Thursday | Attend Meeting | 1 | 1
|  | 1. Add Dashboard API calling service 2. Add emoji in chat (react) | 6 | 6
|  | Total | 7 | 7
19/8/2022 | Friday | Attend Meeting | 1 | 1
|  | Video Demo | 5 | 5
|  | Total | 6 | 6
Note | Minimum 6.5 man-hours per day per person
Fill in the timesheet at the end of the day at 5pm

## Aung Khant
Project | StudyBuddy
Student | Aung Ko Ko Khant
Sprint 0
Spend 0 Duration | 25/7/2022 - 29/7/2022
|  |  | Task | Plan | Actual
| 2022-07-25 | Monday | Attend Briefing | 1 | 1
|  |  | Group Design meeting | 7 | 7
|  |  | Total | 8 | 8
|  |  | Task | Plan | Actual
| 2022-07-26 | Tuesday | attend Meeting | 1 | 1
|  |  | Study RESTful API | 7 | 7
|  |  | Meeting with Prof.Python | 1 | 1
|  |  | Total | 8 | 8
| 2022-07-27 | Wednesday | attend Meeting | 1 | 1
|  |  | Study react | 3 | 3
|  |  | React js | 3 | 3
|  |  | Total | 7 | 7
| 2022-07-28 | Thursday | attend Meeting | 1 | 1
|  |  | Study react | 3 | 3
|  |  | React forms | 3 | 3
|  |  | Total | 7 | 7
| 2022-07-29 | Friday | attend Meeting | 1 | 1
|  |  | Study react | 4 | 4
|  |  | Reactjs | 2 | 2
|  |  | Total | 7 | 7
Sprint 1 duration | 1/8/2022-5/8/2022
| 2022-08-01 | Monday | attend Meeting | 1 | 1
|  |  | Redesign model | 2 | 2
|  |  | Meeting with prof Cher Wah | 1 | 1
|  |  | Total | 3 | 3
| 2022-08-02 | Tuesday | attend Meeting | 1 | 1
|  |  | study react js and api | 6 | 6
|  |  | Total | 7 | 7
| 2022-08-03 | Wednesday | attend Meeting | 1 | 1
|  |  | Data entry and user event for groups | 6 | 6
|  |  | Total | 7 | 7
| 2022-08-04 | Thursday | attend Meeting | 1 | 1
|  |  | testing event and studygroup | 3 | 3
|  |  | fix bugs | 3 | 3
|  |  | Total | 7 | 7
| 2022-08-05 | Friday | attend Meeting | 1 | 1
|  |  | Connect with database | 5 | 5
|  |  | fix bugs | 3 | 3
|  |  | Total | 7 | 7
sprint 2 duration | 8/8/2022-12/8/2022
| 2022-08-08 | Monday | attend Meeting | 1 | 1
|  |  | Meeting with Prof Cher Wah | 1 | 1
|  |  | Study react api and fix bugs | 4 | 4
|  |  | Total | 6 | 6
| 2022-08-09 | Tuesday | National day
| 2022-08-10 | Wednesday | attend Meeting | 1 | 1
|  |  | Fix UI issue in React | 5 | 5
|  |  | Total | 6 | 6
| 2022-08-11 | Thursday | attend Meeting | 1 | 1
|  |  | android redesign | 6 | 6
|  |  | Total | 7 | 7
| 2022-08-12 | Friday | attend Meeting | 1 | 1
|  |  | Try for gif and big stickers | 6 | 6
|  |  | Total | 7 | 7
sprint 3 duration | 15/8/2022-19/8/2022
| 2022-08-15 | Mondy | attend Meeting | 1 | 1
|  |  | bug fix for Gif | 6 | 6
|  |  | Total | 7 | 7
| 2022-08-16 | Tuesday | attend Meeting | 1 | 1
|  |  | Testing chat (emoji and Gif) | 6 | 6
|  |  | Total | 7 | 7
| 2022-08-17 | Wednesday | attend Meeting | 1 | 1
|  |  | Prepare for presentation(Group discussion for presentaion and video) | 5 | 5
|  |  | Total | 6 | 6
| 2022-08-18 | Thursday | attend Meeting | 1 | 1
|  |  | Testing | 2 | 2
|  |  | Preprare video presentation | 3 | 3
|  |  | Total | 6 | 6
| 2022-08-19 | Friday | attend Meeting | 1 | 1
|  |  | Final edit for UI | 3 | 3
|  |  | Record video presentation | 3 | 3
|  |  | Total | 7 | 7

## Zhao Ziyou
Project | StudyBuddy
Student | Zhao Ziyou
Sprint 0 Duration | 25/7/2022 - 29/7/2022
|  | Task | Plan | Actual
2022-07-25 | Monday | Attend Briefing | 1 | 1
|  | Group Design meeting | 7 | 7
|  | Total | 8 | 8
2022-07-26 | Tuesday | domain(model) | 4 | 4
|  | study react js | 2.5 | 2.5
|  | Meeting with Prof Cher Wah | 1 | 1
|  | Total | 7.5 | 7.5
2022-07-27 | Wednesday | Event API+service+Repo | 3 | 3
|  | User API+service+Repo | 3 | 3
|  | study react js | 2 | 2
|  | Total | 8 | 8
2022-07-28 | Thursday | Message API+service+Repo | 3 | 3
|  | Book API+service+Repo | 3 | 3
|  | study react js | 2 | 2
|  | Total | 8 | 8
2022-07-29 | Friday | Email Service+Test Controller for functional testing | 4 | 4
|  | Validation Exception+book validation+user validation | 4 | 4
|  | Total | 8 | 8
Sprint 1 Duration | 1/8/2022 - 5/8/2022
2022-08-01 | Monday | Redesign model | 6 | 6
|  | Meeting with Prof Cher Wah | 0.5 | 0.5
|  | Total | 6.5 | 6.5
2022-08-02 | Tuesday | study react js and add event API caller | 7 | 7
|  | Total | 7 | 7
2022-08-03 | Wednesday | solve name convention and url issue | 3.5 | 3.5
|  | Fix serializer issue, add join study group API. | 3.5 | 3.5
|  | Total | 7 | 7
2022-08-04 | Thursday | Thymeleaf for dashboard | 6.5 | 6.5
|  | Total | 6.5 | 6.5
2022-08-05 | Friday | registration activity and layout | 3.5 | 3.5
|  | forget password activity and layout | 3.5 | 3.5
|  | Total | 7 | 7
Sprint 2 Duration | 8/8/2022 - 12/8/2022
2022-08-08 | Monday | interest layout and activity | 3 | 3
|  | interest fetching and binding | 3.5 | 3.5
|  | Meeting with Prof Cher Wah | 0.5 | 0.5
|  | Total | 7 | 7
2022-08-09 | Tuesday | NATIONAL DAY
2022-08-10 | Wednesday | upload profile image for android part | 8 | 8
|  | Total | 8 | 8
2022-08-11 | Thursday | search for users backend and android part | 7 | 7
|  | Total | 7 | 7
2022-08-12 | Friday | join event/group backend and android part | 4 | 4
|  | send gif to react | 4 | 4
|  | Total | 8 | 8
Sprint 3 Duration | 15/8/2022 - 19/8/2022
2022-08-15 | Monday | add send email for register and forget password | 2 | 2
|  | Bug fixes and testing | 4 | 4
|  | Meeting with Prof Cher Wah | 0.5 | 0.5
|  | Total | 6.5 | 6.5
2022-08-16 | Tuesday | Bug fixes and testing | 2 | 2
|  | Reports for final submission(API file) | 5 | 5
|  | Total | 7 | 7
2022-08-17 | Wednesday | Bug fixes and testing | 2 | 2
|  | Reports for final submission(sequence diagram+UI design) | 4 | 4
|  | Prepare for presentation | 1 | 1
|  | Total | 7 | 7
2022-08-18 | Thursday | Reports for final submission(UI design+sequence diagram) | 6 | 6
|  | Prepare for presentation | 1 | 1
|  | Total | 7 | 7
2022-08-19 | Friday | Take presentation vedio | 2 | 2
|  | Reports for final submission(Combine) | 2 | 2
|  | Make presentation slides | 2 | 2
|  | Combine presentation video | 2 | 2
|  | Total | 8 | 8
Note | Minimum 6.5 man-hours per day per person
Fill in the timesheet at the end of the day at 5pm

## Xie Tingting
Project | StudyBuddy
Student | Xie Tingting
Sprint 0 Duration | 25/7/2022 - 29/7/2022
|  | Task | Plan | Actual
2022-07-25 | Monday | Attend Briefing | 1 | 1
|  | Group Design meeting | 7 | 7
|  | Total | 8 | 8
2022-07-26 | Tuesday | domain(model) | 4 | 4
|  | study rest controller CRUD | 2 | 2
|  | Meeting with Prof Cher Wah | 1 | 1
|  | Total | 7 | 7
2022-07-27 | Wednesday | StudyGroup service+Repo+Controller | 4 | 4
|  | study react js | 2.5 | 2.5
|  | Total | 6.5 | 6.5
2022-07-28 | Thursday | StudyGroup Validator | 3 | 3
|  | Message validator | 3 | 3
|  | study react js | 1 | 1
|  | Total | 7 | 7
2022-07-29 | Friday | attempt calendar layout and activity | 5 | 5
|  | study API | 2 | 2
|  | Total | 7 | 7
Sprint 1 duration | 1/8/2022-5/8/2022
2022-08-01 | Monday | Redesign model | 6.5 | 6.5
|  | Meeting with prof Cher Wah | 0.5 | 0.5
|  | Total | 7 | 7
2022-08-02 | Tuesday | User controller with http status | 3 | 3
|  | Studygroup controller with http status | 3 | 3
|  | Total | 6 | 6
2022-08-03 | Wedneaday | testing event and studygroup with postman | 7 | 7
|  | Total | 7 | 7
2022-08-04 | Thursday | add studygroupDTO | 2 | 2
|  | fix bugs | 1 | 1
|  | edit studygroup controller | 5 | 5
|  | Total | 8 | 8
2022-08-05 | Friday | add interest in userDTO and userController | 2 | 2
|  | testing on postman | 5 | 5
|  | Total | 7 | 7
sprint 2 duration | 8/8/2022-12/8/2022
2022-08-08 | Monday | add event sorting by date | 6.5 | 6.5
|  | Meeting with Prof Cher Wah | 0.5 | 0.5
|  | Total | 7 | 7
2022-08-09 | Tuesday | National day
2022-08-10 | Wednesday | android redesign icon images | 6.5 | 6.5
|  | Total | 6.5 | 6.5
2022-08-11 | Thursday | android redesign chat pop up layout | 7 | 7
|  | Total | 7 | 7
2022-08-12 | Friday | android chat with send url layout | 4 | 4
|  | android chat handle url links | 4 | 4
|  | Total | 8 | 8
sprint 3 duration | 15/8/2022-19/8/2022
2022-08-15 | Mondy | meeting with prof CherWah | 0.5 | 0.5
|  | testing | 6 | 6
|  | Total | 6.5 | 6.5
2022-08-16 | Tuesday | testing | 6.5 | 6.5
|  | Total | 6.5 | 6.5
2022-08-17 | Wednesday | testing | 2 | 2
|  | Reports for final submission(sequence diagram+UI design) | 5 | 5
|  | Total | 7 | 7
2022-08-18 | Thursday | Reports for final submission(sequence diagram+UI design) | 6 | 6
|  | Prepare for presentation | 1 | 1
|  | Total | 7 | 7
2022-08-19 | Friday | Record video for submission | 2 | 2
|  | Description for UI design | 5 | 5
|  | Total | 7 | 7
Note | Minimum 6.5 man-hours per day per person
Fill in the timesheet at the end of the day at 5pm